# Gantt chart

### WP1 — Project setup and disease background

| Task | Output | Owner | Duration (days) | Pred. | Accomplished when |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Defined project objectives and scope | Clara | 2 | - | Objectives are agreed by all four members and match the project requirements |
| 1.2 | Designed Gantt Chart structure | Everybody | 2 | - | Tasks and work packages are defined. Expected start and end dates are defined for each task |
| 1.3 | Organised GitHub/document structure | Vero | 1 | - | All members can access the repository and the paper structure is established |
| 1.4 | Reliable sources on OAT deficiency collected | Clara | 2 | - | At least the key scientific sources needed for the disease background have been identified |
| 1.5 | OAT biological function defined | Vero | 1 | 1.4 | Function, localization and biological role are supported by reliable sources |

### WP2 — OAT gene and disease-associated variants

| Task | Output | Owner | Duration | Pred. | Accomplished when |
| --- | --- | --- | --- | --- | --- |
| 2.1 | OAT gene and reference sequence identified | Clara | 1 | 1.4 | Reference sequence and relevant database information are identified |
| 2.2 | Relevant disease-associated variants identified | Roger | 1 | 2.1 | Variants relevant to OAT deficiency are selected and supported by sources |
| 2.3 | Wild-type vs mutant sequences compared | Vero | 1 | 2.2 | Relevant sequence differences have been identified and documented |
| 2.4 | Biological relevance of sequence differences interpreted | Ana | 1 | 2.3 | The possible consequences of the selected changes are explained using evidence |

### WP3 — Protein structure and PDB analysis

| Task | Output | Owner | Duration | Pred. | Accomplished when |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Suitable OAT structures in PDB identified | Vero | 1 | 2.4 | Appropriate OAT structures have been identified and their limitations documented |
| 3.2 | Relevant mutations in the protein structure are located | Ana | 1 | 3.1 | Selected mutations are mapped onto the protein structure |
| 3.3 | Possible structural consequences are analysed | Roger | 1 | 3.2 | Possible effects on protein structure/function are described and supported by evidence |
| 3.4 | Structural figures are prepared | Roger | 1 | 3.3 | Figures clearly show the relevant structural information and are properly labelled |

### WP4 — Comparative analysis between species

| Task | Output | Owner | Duration | Pred. | Accomplished when |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Two relevant non-human species are selected and information about them is complied | Ana | 1 | 3.4 | Two species have been selected and their relevance explained |
| 4.2 | OAT homologous sequences are obtained | Ana | 1 | 4.1 | Comparable sequences have been obtained from reliable databases |
| 4.3 | Sequence alignment performed | Clara | 1 | 4.2 | Alignment is complete and relevant conserved/divergent regions identified |
| 4.4 | Biological implications have been analysed | Clara | 1 | 4.3 | Conserved and divergent regions are linked to possible functional implications |

### WP5 — Biological interpretation and disease mechanism

| Task | Output | Owner | Duration | Pred. | Accomplished when |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Genetic changes with protein changes are connected | Clara | 1 | 4.4 | Relevant mutations are linked to changes in protein sequence/structure |
| 5.2 | Protein changes with OAT function are connected | Roger | 1 | 5.1 | The relationship between altered OAT and biological function is clearly explained |
| 5.3 | Altered function with disease phenotype are connected | Roger | 1 | 5.2 | The molecular changes are connected to the biological consequences of OAT deficiency |
| 5.4 | Human and species comparison is integrated | Ana | 1 | 5.3 | Species comparison is incorporated into the overall biological interpretation |

### WP6 — Integration, writing and final revision

| Task | Output | Owner | Duration | Pred. | Accomplished when |
| --- | --- | --- | --- | --- | --- |
| 6.1 | All sections are integrated | Vero | 1 | 5.4 | All sections are present and logically connected |
| 6.2 | Scientific consistency is checked | Everybody | 1 | 6.1 | Claims, figures, sequences and interpretations have been checked |
| 6.3 | References and formatting have been revised | Vero | 1 | 6.2 | All sources are correctly cited and the paper follows the required format |
| 6.4 | Final proofreading | Everybody | 1 | 6.3 | Grammar, structure, figures, references and requirements have been checked |
| 6.5 | Final submission | Ana | 1 | 6.4 | Final document is submitted before the deadline |