## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Disease Project: Orthorine Aminotransferase Deficiency
PROJECT MANAGER |  | Veronica Wangchen | [7 empty] | DATE |  |  |  |  | 2026-09-28
WP NUMBER | TASK TITLE | TASK OWNER | START DATE | END DATE | ACTUAL START DATE | ACTUAL END DATE | PREDECESSOR | DURATION | STATUS | PHASE ONE | [9 empty] | PHASE TWO | [5 empty] | PHASE THREE
[10 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 4
[10 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
WP1 | Project initiation and background
1.1 | Define project objectives and risks | Clara | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | - | 1 | 100% | bar: WEEK 1 T to WEEK 1 W
1.2 | Design Gantt Chart structure | Everybody | 2026-10-01 | 2026-10-03 | 2026-10-01 | 2026-10-04 | - | 3 | 100% | bar: WEEK 1 W to WEEK 2 M
1.3 | Organise GitHub | Vero | 2026-10-28 | 2026-10-29 | 2026-10-28 | 2026-10-29 | - | 1 | 100% | bar: WEEK 1 M to WEEK 1 T
1.4 | Find reliable source on OAT | Clara | 2026-09-29 | 2026-10-01 | 2026-09-29 | 2026-10-01 | - | 2 | 95% | bar: WEEK 1 T to WEEK 1 W
1.5 | Define OAT biological function | Vero | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | 1.4 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
WP2 | OAT and the mutant variants
2.1 | Identify the OAT gene and reference sequence | Clara | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | 1.4 |  | 100% | bar: WEEK 2 T to WEEK 2 W
2.2 | Identify relevant variants for the disease | Roger | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-08 | 2.1 | bar: WEEK 2 R
2.3 | Compare wild-type and mutant sequences | Vero | 2026-10-07 | 2026-10-08 | 2026-10-08 |  | 2.2 |  | 50%
2.4 | Interpret the relevance of the sequence differences | Ana | 2026-10-08 | 2026-10-09 |  |  | 2.3
WP3 | The protein structure and PDB analysis
3.1 | Identify OAT structures in PDB | Vero | 2026-10-08 | 2026-10-09 |  |  | 2.4
3.2 | Locate relevant mutations in the protein structure | Ana | 2026-10-09 | 2026-10-12 |  |  | 3.1
3.3 | Analyse the possible structural consequences | Roger | 2026-10-12 | 2026-10-13 |  |  | 3.2
3.4 | Prepare structural figures | Roger | 2026-10-12 | 2026-10-13 |  |  | 3.3
WP4 | Comparison between species
4.1 | Select two relevant non-human species and information about it | Ana | 2026-10-13 | 2026-10-14 | 2026-10-08 |  | 3.4 |  | 80%%
4.2 | Obtain the OAT homolgs sequences | Ana | 2026-10-14 | 2026-10-15 | 2026-10-08 | 2026-10-08 | 4.1 |  | 100% | bar: WEEK 2 R
4.3 | Perform sequence alignment | Clara | 2026-10-15 | 2026-10-16 |  |  | 4.2
4.4 | Analyse the biological implications | Clara | 2026-10-15 | 2026-10-16 |  |  | 4.3
WP5 | Interpretation and disease mechanism
5.1 | Connect the genetic changes with the protein changes | Clara | 2026-10-16 | 2026-10-19 |  |  | 4.4
5.2 | Connect the protein changes with OAT function | Roger | 2026-10-16 | 2026-10-19 |  |  | 5.1
5.3 | Connect the altered function with disease phenotype | Roger | 2026-10-19 | 2026-10-20 |  |  | 5.2
5.4 | Integrate the human and species analysis | Ana | 2026-10-20 | 2026-10-21 |  |  | 5.3
WP6 | Final revision
6.1 | Make sure all sections are present and logically presented | Vero | 2026-10-20 | 2026-10-21 |  |  | 5.4
6.2 | Check scientific consistency | Everybody | 2026-10-20 | 2026-10-21 |  |  | 6.1
6.3 | Revise references and formatting | Vero | 2026-10-21 | 2026-10-22 |  |  | 6.2
6.4 | Final proofreeding | Everybody | 2026-10-23 | 2026-10-26 |  |  | 6.3
6.5 | Final submission | Ana | 2026-10-23 | 2026-10-26 |  |  | 6.4